## Sheet1
Sl | Task | Owner | Timeline
1 | Inform Captain Hassan about InfoHybrid | Fateh | 2018-12-15
2 | Take asfary project under InfoHybrid | Fateh | 2018-12-16
1 | Merge login management of packages module, blog and travel engine | Rajeev | 2018-12-18
4 | Develop Admin Panel for OTA | Rajeev | 2018-12-27 | Take freelance developer
2 | TBO integration | Niraj | 2018-12-27
3 | Voice Search POC | Rajeev | 2018-01-15 | Search, filter, booking with stored card. Interactive wherein lady voice will ask for date, speak cheapest fare found on which airline and time
4 | IBM Watson POC | Niraj | 2018-01-20
5 | NDC POC | Niraj | 2018-02-15